## Project tasks
Project name | Design And Develop a Luggage Tracking Mobile Application For Oman Air - Copy
Project manager | Atheer Oman
Project start date | 2022-03-06
Project finish date | 2023-08-01 17:00
Duration | 367 days
% complete | 0%
Exported on | 2023-06-08 07:29
Task number | Outline number | Name | Duration | Depends on | Start | Finish | Effort remaining | % complete | Bucket | Dependents (after) | Effort | Effort completed | Assigned to | Milestone | Notes | Completed | Checklist Items | Labels | Priority | Sprint
1 | 1 | Chapter 1: Introduction | 80 days |  | 2022-03-07 09:00 | 2022-06-24 17:00 |  | 0% |  | 27FS |  |  |  | No |  |  |  |  | Medium
2 | 1.1 | Introduction | 7 days |  | 2022-03-07 09:00 | 2022-03-15 17:00 |  | 0% |  | 26FS |  |  |  | No |  |  |  |  | Medium
3 | 1.1.1 | Providing background of organization | 7 days |  | 2022-03-07 09:00 | 2022-03-15 17:00 |  | 0% | Bucket 1 | 5FS |  |  |  | No |  |  |  |  | Medium | Backlog
4 | 1.2 | Problem Statement | 32 days |  | 2022-03-16 09:00 | 2022-04-28 17:00 |  | 0% |  | 26FS |  |  |  | No |  |  |  |  | Medium
5 | 1.2.1 | Defining the problem (general and specific) | 7 days | 3FS | 2022-03-16 09:00 | 2022-03-24 17:00 |  | 0% | Bucket 1 | 6FS |  |  |  | No |  |  |  |  | Medium | Backlog
6 | 1.2.2 | Discussing the consequences of the problem | 8 days | 5FS | 2022-03-25 09:00 | 2022-04-05 17:00 |  | 0% | Bucket 1 | 7FS |  |  |  | No |  |  |  |  | Medium | Backlog
7 | 1.2.3 | Suggesting solutions for each problem | 7 days | 6FS | 2022-04-06 09:00 | 2022-04-14 17:00 |  | 0% | Bucket 1 | 8FS |  |  |  | No |  |  |  |  | Medium | Backlog
8 | 1.2.4 | Justifying the project | 5 days | 7FS | 2022-04-15 09:00 | 2022-04-21 17:00 |  | 0% | Bucket 1 | 9FS |  |  |  | No |  |  |  |  | Medium | Backlog
9 | 1.2.5 | Referring to established knowledge (can cite sources) | 5 days | 8FS | 2022-04-22 09:00 | 2022-04-28 17:00 |  | 0% | Bucket 1 | 11FS |  |  |  | No |  |  |  |  | Medium | Backlog
10 | 1.3 | Scope | 22 days |  | 2022-04-29 09:00 | 2022-05-30 17:00 |  | 0% |  | 26FS |  |  |  | No |  |  |  |  | Medium
11 | 1.3.1 | Mentioning the impact of the project on people | 4 days | 9FS | 2022-04-29 09:00 | 2022-05-04 17:00 |  | 0% | Bucket 1 | 12FS |  |  |  | No |  |  |  |  | Medium | Backlog
12 | 1.3.2 | Mentioning the duration | 2 days | 11FS | 2022-05-05 09:00 | 2022-05-06 17:00 |  | 0% | Bucket 1 | 13FS |  |  |  | No |  |  |  |  | Medium | Backlog
13 | 1.3.3 | Stating the cost | 8 days | 12FS | 2022-05-09 09:00 | 2022-05-18 17:00 |  | 0% | Bucket 1 | 14FS |  |  |  | No |  |  |  |  | Medium | Backlog
14 | 1.3.4 | Mentioning the software used | 3 days | 13FS | 2022-05-19 09:00 | 2022-05-23 17:00 |  | 0% | Bucket 1 | 15FS |  |  |  | No |  |  |  |  | Medium | Backlog
15 | 1.3.5 | Describing the features of the application | 5 days | 14FS | 2022-05-24 09:00 | 2022-05-30 17:00 |  | 0% | Bucket 1 | 17FS |  |  |  | No |  |  |  |  | Medium | Backlog
16 | 1.4 | Stakeholders | 4 days |  | 2022-05-31 09:00 | 2022-06-03 17:00 |  | 0% |  | 20FS, 26FS |  |  |  | No |  |  |  |  | Medium
17 | 1.4.1 | Defining terms | 2 days | 15FS | 2022-05-31 09:00 | 2022-06-01 17:00 |  | 0% | Bucket 1 | 18FS |  |  |  | No |  |  |  |  | Medium | Backlog
18 | 1.4.2 | Tabulating the list of stakeholders | 2 days | 17FS | 2022-06-02 09:00 | 2022-06-03 17:00 |  | 0% | Bucket 1 | 20FS |  |  |  | No |  |  |  |  | Medium | Backlog
19 | 1.5 | Interfaces | 4 days |  | 2022-06-06 09:00 | 2022-06-09 17:00 |  | 0% |  | 22FS, 26FS |  |  |  | No |  |  |  |  | Medium
20 | 1.5.1 | Mentioning the external interfaces | 4 days | 16FS, 18FS | 2022-06-06 09:00 | 2022-06-09 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog
21 | 1.6 | Aims and Objectives | 4 days |  | 2022-06-10 09:00 | 2022-06-15 17:00 |  | 0% |  | 26FS |  |  |  | No |  |  |  |  | Medium
22 | 1.6.1 | Stating the aim | 2 days | 19FS | 2022-06-10 09:00 | 2022-06-13 17:00 |  | 0% | Bucket 1 | 23FS |  |  |  | No |  |  |  |  | Medium | Backlog
23 | 1.6.2 | Stating the objectives | 2 days | 22FS | 2022-06-14 09:00 | 2022-06-15 17:00 |  | 0% | Bucket 1 | 25FS |  |  |  | No |  |  |  |  | Medium | Backlog
24 | 1.7 | Contribution | 2 days |  | 2022-06-16 09:00 | 2022-06-17 17:00 |  | 0% |  | 26FS |  |  |  | No |  |  |  |  | Medium
25 | 1.7.1 | Stating the contribution of the project | 2 days | 23FS | 2022-06-16 09:00 | 2022-06-17 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog
26 | 1.8 | Outlining the structure of the report | 5 days | 2FS, 4FS, 10FS, 16FS, 19FS, 21FS, 24FS | 2022-06-20 09:00 | 2022-06-24 17:00 |  | 0% | Bucket 1 | 29FS |  |  |  | No |  |  |  |  | Medium | Backlog
27 | 2 | Chapter 2: Literature Review and Feasibility Analysis | 38 days | 1FS, 37FS, 66FS, 76FS, 95FS | 2023-06-09 09:00 | 2023-08-01 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
28 | 2.1 | Introduction | 12 days |  | 2023-06-09 09:00 | 2023-06-26 17:00 |  | 0% |  | 31FS |  |  |  | No |  |  |  |  | Medium
29 | 2.1.1 | Providing background | 7 days | 26FS | 2023-06-09 09:00 | 2023-06-19 17:00 |  | 0% | Bucket 1 | 30FS |  |  |  | No |  |  |  |  | Medium | Backlog
30 | 2.1.2 | Outlining the structure of the chapter | 5 days | 29FS | 2023-06-20 09:00 | 2023-06-26 17:00 |  | 0% | Bucket 1 | 32FS |  |  |  | No |  |  |  |  | Medium | Backlog
31 | 2.2 | Similar work | 1 day | 28FS | 2023-06-27 09:00 | 2023-06-27 17:00 |  | 0% |  | 33FS |  |  |  | No |  |  |  |  | Medium
32 | 2.2.1 | Describing similar applications (with citations) | 1 day | 30FS | 2023-06-27 09:00 | 2023-06-27 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog
33 | 2.3 | Reviewing literature | 20 days | 31FS | 2023-06-28 09:00 | 2023-07-25 17:00 |  | 0% | Bucket 1 | 35FS, 34FS |  |  |  | No |  |  |  |  | Medium | Backlog
34 | 2.4 | Feasibility Analysis | 5 days | 33FS | 2023-07-26 09:00 | 2023-08-01 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
35 | 2.4.1 | Explaining feasibility analysis | 2 days | 33FS | 2023-07-26 09:00 | 2023-07-27 17:00 |  | 0% | Bucket 1 | 36FS |  |  |  | No |  |  |  |  | Medium | Backlog
36 | 2.4.2 | Describing each type of feasibility analysis | 3 days | 35FS | 2023-07-28 09:00 | 2023-08-01 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog
37 | 3 | Chapter 3: Methodology | 98 days |  | 2022-03-07 09:00 | 2022-07-20 17:00 |  | 0% |  | 27FS |  |  |  | No |  |  |  |  | Medium
38 | 3.1 | Introduction | 4 days |  | 2022-03-07 09:00 | 2022-03-10 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
39 | 3.1.1 | Restating the aim of the project | 2 days |  | 2022-03-07 09:00 | 2022-03-08 17:00 |  | 0% | Bucket 1 | 40FS |  |  |  | No |  |  |  |  | Medium | Backlog
40 | 3.1.2 | Stating the structure of this chapter | 2 days | 39FS | 2022-03-09 09:00 | 2022-03-10 17:00 |  | 0% | Bucket 1 | 41FS, 42FS |  |  |  | No |  |  |  |  | Medium | Backlog
41 | 3.2 | SWOT Analysis for Methodology | 10 days | 40FS | 2022-03-11 09:00 | 2022-03-24 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
42 | 3.2.1 | Analysing each methodology | 10 days | 40FS | 2022-03-11 09:00 | 2022-03-24 17:00 |  | 0% | Bucket 1 | 43FS, 44FS |  |  |  | No |  |  |  |  | Medium | Backlog
43 | 3.3 | Justifying methodology | 14 days | 42FS | 2022-03-25 09:00 | 2022-04-13 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
44 | 3.3.1 | Comparing the methodologies using parameters in tabular form | 7 days | 42FS | 2022-03-25 09:00 | 2022-04-04 17:00 |  | 0% | Bucket 1 | 45FS |  |  |  | No |  |  |  |  | Medium | Backlog
45 | 3.3.2 | Justifying selected methodology | 7 days | 44FS | 2022-04-05 09:00 | 2022-04-13 17:00 |  | 0% | Bucket 1 | 47FS |  |  |  | No |  |  |  |  | Medium | Backlog
46 | 3.4 | Application methodology | 17 days |  | 2022-04-14 09:00 | 2022-05-06 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
47 | 3.4.1 | Describing the stages of the selected methodology | 7 days | 45FS | 2022-04-14 09:00 | 2022-04-22 17:00 |  | 0% | Bucket 1 | 48FS |  |  |  | No |  |  |  |  | Medium | Backlog
48 | 3.4.2 | Describing the application of the methodology to the system of the current project | 10 days | 47FS | 2022-04-25 09:00 | 2022-05-06 17:00 |  | 0% | Bucket 1 | 50FS |  |  |  | No |  |  |  |  | Medium | Backlog
49 | 3.5 | Project Planning | 18 days |  | 2022-05-09 09:00 | 2022-06-01 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
50 | 3.5.1 | Introducing project planning | 3 days | 48FS | 2022-05-09 09:00 | 2022-05-11 17:00 |  | 0% | Bucket 1 | 51FS |  |  |  | No |  |  |  |  | Medium | Backlog
51 | 3.5.2 | Explaining each aspect of project planning | 3 days | 50FS | 2022-05-12 09:00 | 2022-05-16 17:00 |  | 0% | Bucket 1 | 52FS |  |  |  | No |  |  |  |  | Medium | Backlog
52 | 3.5.3 | Including diagrams/figures/tables and flowcharts | 12 days | 51FS | 2022-05-17 09:00 | 2022-06-01 17:00 |  | 0% | Bucket 1 | 54FS |  |  |  | No |  |  |  |  | Medium | Backlog
53 | 3.6 | Data collection and analysis | 21 days |  | 2022-06-02 09:00 | 2022-06-30 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
54 | 3.6.1 | Describing data collection methods | 4 days | 52FS | 2022-06-02 09:00 | 2022-06-07 17:00 |  | 0% | Bucket 1 | 55FS, 57FS |  |  |  | No |  |  |  |  | Medium | Backlog
55 | 3.6.2 | Justifying data collection method | 4 days | 54FS | 2022-06-08 09:00 | 2022-06-13 17:00 |  | 0% | Bucket 1 | 56FS, 57FS |  |  |  | No |  |  |  |  | Medium | Backlog
56 | 3.6.3 | Describing data analysis methods | 5 days | 55FS | 2022-06-14 09:00 | 2022-06-20 17:00 |  | 0% | Bucket 1 | 57FS |  |  |  | No |  |  |  |  | Medium | Backlog
57 | 3.6.4 | Presenting the findings | 4 days | 54FS, 55FS, 56FS | 2022-06-21 09:00 | 2022-06-24 17:00 |  | 0% | Bucket 1 | 58FS |  |  |  | No |  |  |  |  | Medium | Backlog
58 | 3.6.5 | Interpreting the findings | 4 days | 57FS | 2022-06-27 09:00 | 2022-06-30 17:00 |  | 0% | Bucket 1 | 60FS |  |  |  | No |  |  |  |  | Medium | Backlog
59 | 3.7 | Requirements | 7 days |  | 2022-07-01 09:00 | 2022-07-11 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
60 | 3.7.1 | Describing the various requirements to develop the system | 3 days | 58FS | 2022-07-01 09:00 | 2022-07-05 17:00 |  | 0% | Bucket 1 | 61FS |  |  |  | No |  |  |  |  | Medium | Backlog
61 | 3.7.2 | Tabulating information | 4 days | 60FS | 2022-07-06 09:00 | 2022-07-11 17:00 |  | 0% | Bucket 1 | 63FS |  |  |  | No |  |  |  |  | Medium | Backlog
62 | 3.8 | Illustrations | 7 days |  | 2022-07-12 09:00 | 2022-07-20 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
63 | 3.8.1 | Providing diagrams/tables to illustrate the design | 3 days | 61FS | 2022-07-12 09:00 | 2022-07-14 17:00 |  | 0% | Bucket 1 | 64FS |  |  |  | No |  |  |  |  | Medium | Backlog
64 | 3.8.2 | Providing screenshots of initial prototypes | 4 days | 63FS | 2022-07-15 09:00 | 2022-07-20 17:00 |  | 0% | Bucket 1 | 68FS, 65FS |  |  |  | No |  |  |  |  | Medium | Backlog
65 | 4 | Break | 60 days | 64FS | 2022-07-21 09:00 | 2022-10-12 17:00 |  | 0% | Bucket 1 | 68FS |  |  |  | No |  |  |  |  | Medium | Backlog
66 | 5 | Chapter 4: Design | 41 days |  | 2022-10-13 09:00 | 2022-12-08 17:00 |  | 0% |  | 27FS |  |  |  | No |  |  |  |  | Medium
67 | 5.1 | Introduction | 5 days |  | 2022-10-13 09:00 | 2022-10-19 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
68 | 5.1.1 | Stating the structure of this chapter | 5 days | 64FS, 65FS | 2022-10-13 09:00 | 2022-10-19 17:00 |  | 0% | Bucket 1 | 70FS |  |  |  | No |  |  |  |  | Medium | Backlog
69 | 5.2 | Illustrating the design | 36 days |  | 2022-10-20 09:00 | 2022-12-08 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
70 | 5.2.1 | Illustrating the whole/parts of the system | 10 days | 68FS | 2022-10-20 09:00 | 2022-11-02 17:00 |  | 0% | Bucket 1 | 71FS |  |  |  | No |  |  |  |  | Medium | Backlog
71 | 5.2.2 | Using location statements | 6 days | 70FS | 2022-11-03 09:00 | 2022-11-10 17:00 |  | 0% | Bucket 1 | 72FS |  |  |  | No |  |  |  |  | Medium | Backlog
72 | 5.2.3 | Describing the metadata stored for each entity | 5 days | 71FS | 2022-11-11 09:00 | 2022-11-17 17:00 |  | 0% | Bucket 1 | 73FS |  |  |  | No |  |  |  |  | Medium | Backlog
73 | 5.2.4 | Describing the purpose of each diagram | 5 days | 72FS | 2022-11-18 09:00 | 2022-11-24 17:00 |  | 0% | Bucket 1 | 74FS |  |  |  | No |  |  |  |  | Medium | Backlog
74 | 5.2.5 | Describing security measures | 6 days | 73FS | 2022-11-25 09:00 | 2022-12-02 17:00 |  | 0% | Bucket 1 | 75FS |  |  |  | No |  |  |  |  | Medium | Backlog
75 | 5.2.6 | Screenshots of application (each page) | 4 days | 74FS | 2022-12-05 09:00 | 2022-12-08 17:00 |  | 0% | Bucket 1 | 78FS, 80FS |  |  |  | No |  |  |  |  | Medium | Backlog
76 | 6 | Chapter 5: Development and Evaluation | 98 days |  | 2022-12-09 09:00 | 2023-04-25 17:00 |  | 0% |  | 27FS |  |  |  | No |  |  |  |  | Medium
77 | 6.1 | Introduction | 5 days |  | 2022-12-09 09:00 | 2022-12-15 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
78 | 6.1.1 | Outline of the chapter | 5 days | 75FS | 2022-12-09 09:00 | 2022-12-15 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog
79 | 6.2 | Describing the system | 28 days |  | 2022-12-09 09:00 | 2023-01-17 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
80 | 6.2.1 | Providing a brief description about each page | 5 days | 75FS | 2022-12-09 09:00 | 2022-12-15 17:00 |  | 0% | Bucket 1 | 81FS |  |  |  | No |  |  |  |  | Medium | Backlog
81 | 6.2.2 | Screenshot of each page | 8 days | 80FS | 2022-12-16 09:00 | 2022-12-27 17:00 |  | 0% | Bucket 1 | 82FS |  |  |  | No |  |  |  |  | Medium | Backlog
82 | 6.2.3 | Providing the coding for each page | 15 days | 81FS | 2022-12-28 09:00 | 2023-01-17 17:00 |  | 0% | Bucket 1 | 84FS |  |  |  | No |  |  |  |  | Medium | Backlog
83 | 6.3 | Testing & Evaluation | 25 days |  | 2023-01-18 09:00 | 2023-02-21 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
84 | 6.3.1 | Explaining the importance of testing | 7 days | 82FS | 2023-01-18 09:00 | 2023-01-26 17:00 |  | 0% | Bucket 1 | 85FS |  |  |  | No |  |  |  |  | Medium | Backlog
85 | 6.3.2 | Introducing the test strategy | 4 days | 84FS | 2023-01-27 09:00 | 2023-02-01 17:00 |  | 0% | Bucket 1 | 86FS |  |  |  | No |  |  |  |  | Medium | Backlog
86 | 6.3.3 | Providing information in tables/figures | 4 days | 85FS | 2023-02-02 09:00 | 2023-02-07 17:00 |  | 0% | Bucket 1 | 87FS |  |  |  | No |  |  |  |  | Medium | Backlog
87 | 6.3.4 | Illustrating the test results in a table | 5 days | 86FS | 2023-02-08 09:00 | 2023-02-14 17:00 |  | 0% | Bucket 1 | 88FS |  |  |  | No |  |  |  |  | Medium | Backlog
88 | 6.3.5 | Analysing the test results | 5 days | 87FS | 2023-02-15 09:00 | 2023-02-21 17:00 |  | 0% | Bucket 1 | 90FS |  |  |  | No |  |  |  |  | Medium | Backlog
89 | 6.4 | Deployment | 35 days |  | 2023-02-22 09:00 | 2023-04-11 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
90 | 6.4.1 | Describing the specifications for implementation | 20 days | 88FS | 2023-02-22 09:00 | 2023-03-21 17:00 |  | 0% | Bucket 1 | 91FS |  |  |  | No |  |  |  |  | Medium | Backlog
91 | 6.4.2 | Providing information in tab | 15 days | 90FS | 2023-03-22 09:00 | 2023-04-11 17:00 |  | 0% | Bucket 1 | 93FS |  |  |  | No |  |  |  |  | Medium | Backlog
92 | 6.5 | Critical evaluation | 10 days |  | 2023-04-12 09:00 | 2023-04-25 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
93 | 6.5.1 | Critically evaluating the system | 5 days | 91FS | 2023-04-12 09:00 | 2023-04-18 17:00 |  | 0% | Bucket 1 | 94FS |  |  |  | No |  |  |  |  | Medium | Backlog
94 | 6.5.2 | Providing a checklist of requirements and showing status | 5 days | 93FS | 2023-04-19 09:00 | 2023-04-25 17:00 |  | 0% | Bucket 1 | 97FS |  |  |  | No |  |  |  |  | Medium | Backlog
95 | 7 | Chapter 6: Conclusion and Recommendations | 32 days |  | 2023-04-26 09:00 | 2023-06-08 17:00 |  | 0% |  | 27FS |  |  |  | No |  |  |  |  | Medium
96 | 7.1 | Concluding | 13 days |  | 2023-04-26 09:00 | 2023-05-12 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
97 | 7.1.1 | Restating aim | 3 days | 94FS | 2023-04-26 09:00 | 2023-04-28 17:00 |  | 0% | Bucket 1 | 98FS |  |  |  | No |  |  |  |  | Medium | Backlog
98 | 7.1.2 | Summarising the key results | 3 days | 97FS | 2023-05-01 09:00 | 2023-05-03 17:00 |  | 0% | Bucket 1 | 99FS |  |  |  | No |  |  |  |  | Medium | Backlog
99 | 7.1.3 | Evaluating the contribution of the project (practical applications) | 3 days | 98FS | 2023-05-04 09:00 | 2023-05-08 17:00 |  | 0% | Bucket 1 | 100FS |  |  |  | No |  |  |  |  | Medium | Backlog
100 | 7.1.4 | Discussing the applications of the system | 4 days | 99FS | 2023-05-09 09:00 | 2023-05-12 17:00 |  | 0% | Bucket 1 | 102FS |  |  |  | No |  |  |  |  | Medium | Backlog
101 | 7.2 | Recommendations | 4 days |  | 2023-05-15 09:00 | 2023-05-18 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
102 | 7.2.1 | Recommending future projects in the same area | 4 days | 100FS | 2023-05-15 09:00 | 2023-05-18 17:00 |  | 0% | Bucket 1 | 104FS |  |  |  | No |  |  |  |  | Medium | Backlog
103 | 7.3 | Limitations | 3 days |  | 2023-05-19 09:00 | 2023-05-23 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
104 | 7.3.1 | Stating the limitations of the application | 3 days | 102FS | 2023-05-19 09:00 | 2023-05-23 17:00 |  | 0% | Bucket 1 | 106FS |  |  |  | No |  |  |  |  | Medium | Backlog
105 | 7.4 | Impact of the Project | 12 days |  | 2023-05-24 09:00 | 2023-06-08 17:00 |  | 0% | [5 empty] | No |  |  |  |  | Medium
106 | 7.4.1 | Describing the social impact | 3 days | 104FS | 2023-05-24 09:00 | 2023-05-26 17:00 |  | 0% | Bucket 1 | 107FS |  |  |  | No |  |  |  |  | Medium | Backlog
107 | 7.4.2 | Describing the ethical impact | 3 days | 106FS | 2023-05-29 09:00 | 2023-05-31 17:00 |  | 0% | Bucket 1 | 108FS |  |  |  | No |  |  |  |  | Medium | Backlog
108 | 7.4.3 | Describing the legal impact | 3 days | 107FS | 2023-06-01 09:00 | 2023-06-05 17:00 |  | 0% | Bucket 1 | 109FS |  |  |  | No |  |  |  |  | Medium | Backlog
109 | 7.4.4 | Discussing sustainability aspects | 3 days | 108FS | 2023-06-06 09:00 | 2023-06-08 17:00 |  | 0% | Bucket 1 |  |  |  |  | No |  |  |  |  | Medium | Backlog